|  |
| --- |
| **National Action Plan**Country: Vietnam |
| No. | Action | Anticipated results | Deadline/ Milestones | Responsible |
|  | **Short term** |  |  |  |
| 1 | A training for staff in use of IPP* Select staff for training
* Nominate new editors and members
 | Staff to be chosen and trained as editors* 5 staff members selected
* Training staff
* 1-2 new editors nominated and others to be members
 | Early August | Nguyen Quang HieuHoang TrungHoang Trung |
| 2 | Organize a consultation meeting with relevant agencies for gathering information and updates | Awareness raising for relevant agencies such as: research institutes, universities, policy maker … | 29th July | Hoang TrungNguyen Quang Hieu  |
| 3 | Consolidate and prepare all information following the guidelines | Available information updatedNew information and amendments are collected, updated | End of AugustEnd of 2011 | Nguyen Quang Hieu and other editors |
| 4 | Editors upload all information to IPP after verified by the national contact point | Necessary information to be updated meet IPPC requirementsOverlapped items will be modified/replaced | September  | EditorsEditors |
| 5 | Develop mechanism to exchange information between NPPO and other agencies | Drafting documentsConsolidating commentsAn exchange mechanism are developed, with aim to provide information regularly | End of 2011 | Hoang TrungEditors |
|  | **Longterm** |  |  |  |
| 6 | Ispm 15 | Apply ISPM 15 for importing commodities which cover by WPM | Early 2012 | PPD |
| 7 | New Law draft | New article will be stipulated in gathering information and dissemination as well as coordination mechanism between PDD and relevant agencies | 2013 | PPD |
| 8 | Invest in infrastructure and equipment | A National Database in place and a availability of connection and computers from local to central levels to meet information exchange requirements  | 2015 | PPD |
| 9 | Pest Surveillance | Consolidate data from surveillance for pest status reports, uploading to IPP websites | 2015 | PPD |